## Test cases
Product Name |  | https://www.priyoshop.com/ | TC Start Date | 2024-01-11 | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | Registration and Log In | TC End Date | 2024-01-12 | TC Execution End Date | [5 empty] | PASS | 39
Epic |  |  | Test Case Developed By | Kazi Sultana Margia | Browser (tested) | No |  |  |  |  | FAIL | 9
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | out of Scope | 0
[11 empty] | Total | 48
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 | User Management | UI Testing | Register | Checking spelling and gram | No spelling or grammatical mistakes | Found as per expectation | N / A | Go to url www.priyoshop.com |  |  | Passed
2 |  |  |  | Checking structure of field. | Should be as per the requirement | Found as per expectation | N / A | Go to url www.priyoshop.com |  |  | Passed
3 |  |  |  | Verifying mandatory field is marked with a red asterisk. | Red asterisk should be present | Found as per expectation | N / A | Go to url www.priyoshop.com |  |  | Passed
4 |  |  |  | Checking the required field is clickable. | A text should appear over the fields | Found as per expectation | N / A | Go to url www.priyoshop.com |  |  | Passed
5 |  |  |  | Checking color of field | Color should be as per requirement | Found as per expectation | N / A | Go to url www.priyoshop.com |  |  | Passed
6 |  |  |  | Checking alignment of the field | Proper alignment of the fields should be present | Found as per expectation | N / A | Go to url www.priyoshop.com |  |  | Passed
7
8 |  | Functional Testing |  | Verify that medium field is selectable | Should be as per the requirement | Should not allow users to register and pop an error message | N/A | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | Verify that Keeping all the mandatory fields blank | Should be as per the requirement | Should not allow users to register and pop an error message | N/A | Go to url www.priyoshop.com |  |  | Passed
9 |  |  |  | Verify that Name field is case insensitive | Should accept the provided input | Found as per expectation | riCHi | Go to url www.priyoshop.com |  |  | Passed
10 |  |  |  | Entering blank at first position in name field | Should not accept the provided input | not Found as per expectation | efdd | Go to url www.priyoshop.com |  |  | Passed
11 |  |  |  | verify that alert message for all mandatory fields should appear | required message should be showed | found as per expectation | N/A | Go to url www.priyoshop.com |  |  | Passed
12 |  |  |  | verify that Inputting name with special characters | Should not accept the provided input | Not found as per expectation | @@## | Go to url www.priyoshop.com |  |  | Passed
14 |  |  |  | verify that Inputing name with numbers | Should not accept the provided input | Not found as per expectation | 232313 | Go to url www.priyoshop.com |  |  | Passed
15 |  |  |  | verify that Inputing name with alphanumeric characters | Should accept the provided input | Found as per expectation | pk88 | Go to url www.priyoshop.com |  |  | Passed
18 |  |  |  | Entering comma between alphabets in name | Should not accept the provided input | Not found as per expectation | re,bert | Go to url www.priyoshop.com |  |  | Passed
19 |  |  |  | Entering space between alphabets for name | Should accept the provided input | Found as per expectation | steve brown | Go to url www.priyoshop.com |  |  | Passed
20 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | margiarichi@gmail.com | Go to url www.priyoshop.com |  |  | Passed
21 |  |  |  | verify that inputing invalid email format | Should not accept the provided input and display an error message | Found as not expectation | vaabshaab@fsfhsfdsf.com | Go to url www.priyoshop.com |  |  | Passed
23 |  |  |  | verify that inputing valid email format | Should accept the provided input | Found as per expectation | richisultana62@gmail.com | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | Verify that input valid phone number | Should accept the provided input | Found as per expectation | 1611590156 | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | Verify that input invalid phone number | Should accept the provided input | Found as per expectation | 016115901t6 | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | verify that input phone number with limit | Should accept the provided input | Found as per expectation | 1611590156 | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | Verify that input phone number with large length | Should accept the provided input | Not found as per expectation | 0 18976543212 | Go to url www.priyoshop.com | Large length of number |  | Failed
|  |  |  | Verify that input phone number with Small length | Should accept the provided input | Not found as per expectation | 0 161 | Go to url www.priyoshop.com | Small lenth of number |  | Failed
24 |  |  |  | verify that Checking password and confirm field values are masked | Should be masked | Found as per expectation | mean999 | Go to url www.priyoshop.com |  |  | Passed
25 |  |  |  | Inputing invalid combinations of characters in password and confirm password field | Should not allow user to register and display a pop message | Found as per expectation | Rohn7777 | Go to url www.priyoshop.com |  |  | Passed
26 |  |  |  | verify that Inputing weak password length | Should allow user to register | Found as per expectation | 4444 | Go to url www.priyoshop.com | invalid password |  | Failed
27 |  |  |  | verify that Inputing medium password length | Should allow user to register | Found as per expectation | 1111@@# | Go to url www.priyoshop.com |  |  | Passed
28 |  |  |  | verify that Inputing strong password length | Should allow user to register | Found as per expectation | Sr2288@@#### | Go to url www.priyoshop.com |  |  | Passed
29 |  |  |  | Verify that Inputing different data for password and confirm password | Should not allow user to register and display a pop message | Found as per expectation | password: richi123# Confirm password:richi@123 | Go to url www.priyoshop.com | Does not match |  | Failed
30 |  |  |  | Verify that Inputing valid data for password and confirm password | Should allow user to register | Found as per expectation | password: richi123# Confirm password:richi123# | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | Verify that inputing street address field with number | Should accept the provided input | Found as per expectation | 55555 | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | Verify that inputing street address field with special character and number | Should accept the provided input | Found as per expectation | #%se&AA12 | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | verify that inputing country field is selectable | Should accept the provided input | Found as per expectation | Bangladesh | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | verify that inputing district field is selectable | Should accept the provided input | Found as per expectation | feni | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | verify that inputing police stations field is selectable | Should accept the provided input | Found as per expectation | fulgazi | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | verify that inputing country field is globaly selectable | Should accept the provided input | Found as per expectation | portugal | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | Verify that inputing district field is globally selectable | Should accept the provided input | Not found as per expectation |  | Go to url www.priyoshop.com | invalid district |  | Failed
|  |  |  | Verify that inputing Police stations field is globally selectable | Should accept the provided input | Not found as per expectation |  | Go to url www.priyoshop.com | invalid police station |  | Failed
|  |  |  | verify that privacy policy is work without click | Should accept the provided input | Not Found as per expectation with an error message | N/A | Go to url www.priyoshop.com | Not accept terms policy |  | Failed
|  |  |  | verify that privacy policy clickable | Should accept the provided input | Found as per expectation with an error message | N/A | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | Verify that registration button with valid credentials phone | Should allow user to register | Found as per expectation | Name: Richi Phone:01824345674 Password: ric66@@##44 Confirm Password: ric66@@##43 |  |  |  | Passed
31 |  |  |  | Verify that registration button with valid credentials email | Should allow user to register | Found as per expectation | Name: Richi Email:Richi66@gmail.com Password: ric66@@##44 Confirm Password: ric66@@##44 | Go to url www.priyoshop.com |  |  | Passed
|  |  |  | Checking confirmation mail sent to the registered email | Sent successfully | Found as per expectation | Name: Robert Email:Robert55@gmail.com Password: rob66@@##44 Confirm Password: rob66@@##43 | Go to url www.priyoshop.com |  |  | Failed
45
|  |  | Log In | Checking login function is workable | Should allow user to register | Not Found as per expectation with an error message |  | Go to url www.priyoshop.com | Log in internal error |  | Failed
47 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | efef3434 | 1. Goto the URL https:// www.priyoshop.com/ 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
|  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https:// www.priyoshop.com/ 2. Click on Register button at the right corner 3. Enter tab in every field |  |  | Passed
|  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1. Goto the URL https:// www.priyoshop.com/ 2. Click on Register button at the right corner 3. Enter in every field |  |  | Passed
|  |  | Improvement scope | 'Remember Me' checkbox should be selected according to user
A maximum length of the password should be defined
Place 'Whats this?' below 'Remember Me'
a eye icon is added in the password field
Sign with google and all social options

## Mind maps
Mindmaps for PriyoShop.com website Testing

## Report
Test Case Report
Project Name | PriyoShop.com
Module Name | Sign Up and Sign In |  |  |  |  | Status | Test Case no
Test Case Version | [5 empty] | PASS | 39
Written By | Kazi Sultana Margia |  |  |  |  | FAIL | 9
Executed By | Kazi Sultana Margia |  |  |  |  | Not Executed | 0
Reviewed By | [5 empty] | Out of Scope | 0
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 39 | 9 | 0 | 0 | 48
Grand Total | 39 | 9 | 0 | 0 | 48

## Bug Report
Bug Reporting
SL#33
Issue:Entering Phone number with large length
Reproducing Steps:
1. Go to URL: www.PriyoShop.com
2. Click the button "registration"
4. Input large length digit of Phone number field
Module: Registration
Severity: P2
Image: Large length of number
Responsible QA: Kazi Sultana Margia.
Bug Reporting
SL#34
Issue:Entering Phone number with large length
Reproducing Steps:
1. Go to URL: www.PriyoShop.com
2. Click the button "registration"
4. Input small length digit of Phone number field
Module: Registration
Severity: P2
Image: Small length of number
Responsible QA: Kazi Sultana Margia.
Bug Reporting
SL#33
Issue:Entering Phone number with large length
Reproducing Steps:
1. Go to URL: www.PriyoShop.com
2. Click the button "registration"
4. Input weak password length of password field
Module: Registration
Severity: P2
Image: invalid password
Responsible QA: Kazi Sultana Margia.
Bug Reporting
SL#40
Issue:Entering Password does not match
Reproducing Steps:
1. Go to URL: www.PriyoShop.com
2. Click the button "registration"
4. Input Password does not match
Module: Registration
Severity: P2
Image: Password does not match
Responsible QA: Kazi Sultana Margia.
Bug Reporting
SL#48
Issue: Entering district globally selectable
Reproducing Steps:
1. Go to URL: www.PriyoShop.com
2. Click the button "registration"
4. Input district globally in distric field
Module: Registration
Severity: P2
Image: Invalid District
Responsible QA: Kazi Sultana Margia.
Bug Reporting
SL#49
Issue: Entering polic stations globally selectable
Reproducing Steps:
1. Go to URL: www.PriyoShop.com
2. Click the button "registration"
4. Input police station globally in police station field
Module: Registration
Severity: P2
Image: Invalid Police Stations
Responsible QA: Kazi Sultana Margia.
Bug Reporting
SL#50
Issue:Entering term policy without click
Reproducing Steps:
1. Go to URL: www.PriyoShop.com
2. Click the button "registration"
4. Input term policy without click
Module: Registration
Severity: P2
Image: Not accept term policy
Responsible QA: Kazi Sultana Margia.
Bug Reporting
SL#54
Issue: Send to the confirmation mail to the registered mail.
Reproducing Steps:
1. Go to URL: www.PriyoShop.com
2. Click the button "registration"
4. Check the confirmation mail in the registered mail box
Module: Registration
Severity: P2
Responsible QA: Kazi Sultana Margia.
Bug Reporting
SL#56
Issue: Not allow to login for internal error
Reproducing Steps:
1. Go to URL: www.PriyoShop.com
2. Click the button "login "
4. Input term policy without click
Module: login
Severity: P2
Image: internal error
Responsible QA: Kazi Sultana Margia.

## Test Metrix
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (48/48)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/48)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (39/48)*100 = 81.25
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (9/48)*100 = 18.75
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/48)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A
PriyoShop.Com website